## General_Tracker
Data Conversion Open Item Tracker
# | Description | Phase | EY Owner(s) | Fiserv Owner(s) | Status | Notes
1 | Object Tracker - Phase 0 Items | 0 All | Adam Zeckel Callan Loberg |  | Open | - Round 1 sent to Fiserv group by Tom on Thursday, 11/12 - Round 2 sent to Fiserv group by Callan on Tuesday, 11/17 - Round 3 sent to Fiserv group by Callan on Sunday, 11/22 - Round 3 reminder sent to Fiserv group by Callan on Monday, 11/30
2 | Decision: SAP DS/IS for S/4 Data Migration | 0. Prepare | Adam Zeckel Callan Loberg Anshuman Beri |  | Closed | - As part of Phase 0, it was decided that IDS will be pursued in place of SAP DS/IS
3 | EY IDS Approval from Fiserv Cyber Team | 0. Prepare 1. Explore | Adam Zeckel Daniel Nicolotti Callan Loberg Anshuman Beri | Rajan Odayar Martin Wong Prasuna Kurra Earl Manning Roopa Prakash | At Risk | - Details requested from EY India Innovation Team - Callan (11/12) - Rajan O scheduled Fiserv Securiy call for Wed, 11/18 - SAP Certificate received from EY Innovation Team (11/18) - Details for IDS (plus ReSQ and Config Move) sent to Fiserv Security (11/20)
4 | Scope & Ownership of Open Text Archive Migation | 0. Prepare 1. Explore | Callan Loberg Anshuman Beri |  | Closed | - Callan and Beri to discuss during Prep call 11/19 - Open Text will be driven by a separate contract with Open Text. Out of Scope for EY.
5 | Provision EY IDS at Fiserv | 1. Explore | Callan Loberg Anshuman Beri |  | At Risk | - Target Date of Jan 1, 2020. Need ~2 weeks, so looking for Security Approval before Christmas
6 | Existing SAP Address Cleansing Package Setup | 1. Explore | Callan Loberg Anshuman Beri | Roopa Prakash (Data & Integration Lead) Earl Manning (Basis Lead) Krishna Polineni (Basis Architect) Margaret Moloney (Basis Architect) | Closed | - Conferring with Beri on Email to Fiserv (11/18) - Roopa replied with details. Packages do not currently exist at Fiserv (11/19)
7 | Existing D&B Integration Manager Setup | 1. Explore | Callan Loberg Anshuman Beri | Roopa Prakash (Data & Integration Lead) Earl Manning (Basis Lead) Krishna Polineni (Basis Architect) Margaret Moloney (Basis Architect) | Closed | - Conferring with Beri on Email to Fiserv (11/18) - Roopa replied with details. Installed on-prem with file-based integration (11/19)
8 | Shared Folder Setup for Data Extracts | 1. Explore | Callan Loberg Anshuman Beri |  | Open | - Requirement detail sent to Beri. His team will aim to have it by Jan 1, 2021. (11/20)
9 | Publish Example ECC Relevancy Rules to Fiserv | 1. Explore | Callan Loberg |  | Open | - Planning for Second Week of December - Callan 11/20
10 | Publish Full Set of S/4 Templates to Fiserv | 1. Explore | Callan Loberg |  | Open | - Planning for First Week of January - Callan 11/20

## Object_Tracker
S/4HANA Data Object | [6 empty] | Phase 0 (Prepare) Items | [6 empty] | Explore Items | [15 empty] | Available Load Method
[7 empty] | S/4 Data Conversion Scope |  |  | Source System |  | Est. Data Volume |  | Planned Completion |  | Relevancy Rules |  |  | Extract Method to S/4 Template |  |  | Quality Tool |  | EY Internal IDS Tracking |  |  | Load Tool | Cleansing Reference
Conversion Object | Data Type | Object Group | Area | EY Func. Owner | FSV Owner | FDC Owner | FSV | FDC | Notes | FSV | FDC | FSV | FDC | Profiling | Mapping | ECC Example | FSV | FDC | S/4 Template | FSV | FDC | Profile | Information Steward | Rules Count | Rules Test Status | S/4 Mapping Template Status | Load to S/4 | D&B IM | Address | IDS | IDoc | LTMC | Direct | Manual | Program | LSMW
Accounts Receivable Open Item | Transactional | AR | OTC |  | Maria | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS | 12000000 | 27000 | [6 empty] | IDS Direct Connection | File - Standard Program | IDS | Yes | 118 | Unit test done |  | IDS |  |  | X | X | X
Bank Master | Master | Bank | Treasury |  | Pablo | Pablo | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | Yes | 21 | Unit test done |  | IDS |  |  | X | X | X |  | X | X
Condition Record for Pricing | Master | Condition Record | OTC |  | Maria | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 306636 | TBD | [6 empty] | IDS Direct Connection |  | IDS | Yes |  |  |  | IDS |  |  | X | X | X
Customer | Master | Client | OTC/MD |  | Maria/Tom | Vivek | 1 | 1 | Excel/DRM/IDW/UFO | SAP ECC | Oracle EBS | 20000 | 7000 | [6 empty] | IDS Direct Connection |  | IDS | Yes | 94 | Unit test done |  | IDS |  |  | X | X | X
Bank - Balance | Transactional | Bank | Accounting |  | Tom | Tom | TBD | TBD | Uncleared Checks | [13 empty] | No | [8 empty] | X |  |  | X
Customer Classification | Master | Client | MD |  | Tom | Tom | 1 | 1 | FDIC # (Class) | [10 empty] | IDS Direct Connection |  | IDS | No |  |  |  | IDS |  |  | X | X
Fixed Asset (Incl. Balances and Transactions) | Transactional | Fixed Asset | Accounting |  | Tom | Tom | 1 | 1 |  | SAP ECC | Oracle EBS, Excel (CIP) | [8 empty] | IDS Direct Connection |  | IDS | Yes | 45 | Unit test done |  | IDS |  |  | X | X | X
Cash (Credit) Memo Record | Transactional | Bank | Treasury |  | Pablo | Pablo | TBD | TBD | [14 empty] | No | [6 empty] | X | X | X
Class | Master | Client/Vendor | OTC/MD |  | Maria/Tom | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 34 | TBD | [9 empty] | No | [6 empty] | X | X | X
Collections | Transactional | Collections | FSCM |  |  |  | TBD | TBD | [14 empty] | No
Collections (Collectors) | Master | Collections | OTC |  | Maria | Vivek | 1 | 0 | Need Oracle Translator for FDC. | SAP ECC | N/A | 30 | 0 | [9 empty] | No
Condition Contract - Rebate | Master | Rebate | PTP |  | Pablo | Pablo | TBD | TBD | In S/4, rebates are replaced with Condition Contract Management (CCM) | [13 empty] | No
GL Account Balance | Transactional | Account | Accounting |  | Tom | Tom | 1 | 1 |  | SAP ECC | Oracle EBS | 2500 | 5500 | [6 empty] | IDS Direct Connection |  | IDS | Yes |  |  |  | IDS |  |  | X | X | X
COPA Assessments | Master | COPA | Finance |  | Leela | Leela | TBD | TBD | Conversion source might not be from ERP | [12 empty] | N/A | No |  |  |  | TBD | [7 empty] | X
COPA Derivation Rules | Master | COPA | Finance |  | Leela | Leela | TBD | TBD | Conversion source might not be from ERP | [12 empty] | N/A | No |  |  |  | TBD | [7 empty] | X
COPA Value Fields | Master | COPA | Finance |  | Leela | Leela | TBD | TBD | Conversion source might not be from ERP | [12 empty] | N/A | No |  |  |  | TBD | [7 empty] | X
GL Account Open Items | Transactional | Account | Accounting |  | Tom | Tom | 1 | 1 | Review Open Items Counts | SAP ECC | Oracle EBS | [8 empty] | IDS Direct Connection |  | IDS | Yes |  |  |  | IDS |  |  | X | X | X
Goods/Invoice Receipt (GR/IR) Open Items | Transactional | GRIR | PTP |  | Pablo | Pablo | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | No |  |  |  | IDS |  |  | X | X
Intercompany (IC) by Trading Partner | Master | Intercompany | Accounting |  | Tom | Tom | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | No |  |  |  | IDS
Item Proposal | Transactional | Item Proposal | OTC |  | Maria | Vivek | TBD | TBD | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 0 | TBD | [6 empty] | IDS Direct Connection |  | IDS | No |  |  |  | IDS | [7 empty] | X
Dispute Management Tables | Master | FSCM | OTC |  | Maria | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 17685 | TBD | [9 empty] | No |  |  |  | Program
Material | Master | P Material | OTC/PTP |  | Maria/Pablo | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 68597 | TBD | [6 empty] | IDS Direct Connection |  | IDS | Yes | 236 | Unit test done |  | IDS |  |  | X | X | X
Product (Material) BOM | Master | Reseller | OTC/PTP |  | Maria/Pablo | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 231 | TBD | [6 empty] | IDS Direct Connection |  | IDS | Yes | 133 | Unit test done |  | IDS |  |  | X | X | X
Product Inventory IM (Finished) | Transactional | Reseller | OTC/PTP |  | Maria/Pablo | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 3682 | TBD | [6 empty] | IDS Direct Connection |  | IDS | No |  |  |  | IDS |  |  | X | X
Project Budget | Master | IO | Finance |  | Leela | Leela | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | No |  |  |  | IDS
Purchase Info Record with Conditions | Master | P Material | PTP |  | Pablo | Pablo | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | Yes |  |  |  | IDS |  |  | X | X | X
Purchase Order (Open PO) | Transactional | Purchase Order | PTP |  | Pablo | Pablo | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | Yes |  |  |  | IDS |  |  | X | X | X
Sales BOM | Master | S Material | OTC |  | Maria | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 0 | TBD | [6 empty] | IDS Direct Connection |  | IDS | No |  |  |  | IDS |  |  | X | X
Sales Contract | Transactional | Contract | OTC |  | Maria | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 161877 | TBD | [6 empty] | IDS Direct Connection |  | IDS | Yes |  |  |  | IDS |  |  | X | X | X
Supplier (Vendor) | Master | Vendor | PTP |  | Pablo | Pablo | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | Yes | 105 | Unit test done |  | IDS |  |  | X | X | X
Supplier Characteristic | Master | Vendor | PTP |  | Pablo | Pablo | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | No |  |  |  | IDS |  |  | X | X
Internal Order Activity | Transactional | IO | Finance/Acctg |  | Leela/Tom | Leela/Tom | 1 | 1 | [14 empty] | Yes | [6 empty] | X | X | X |  |  | X
Supplier Invoice (Only Open)/ AP Open | Transactional | Invoice | PTP |  | Pablo | Pablo | TBD | TBD | [11 empty] | IDS Direct Connection |  | IDS | Yes | 114 | Unit test done |  | IDS |  |  | X | X
Lease Related Items - CLM | Transactional | CLM |  |  |  |  | TBD | TBD | Contract & Lease Management (CLM) | [12 empty] | None | No
EDI Partner (ALE) | Transactional | Technical | Technical |  | Roopa | Roopa | 1 | 0 |  | SAP ECC | N/A | 39 | 0 | [6 empty] | IDS Direct Connection |  | IDS | No |  |  |  | LSMW | [7 empty] | X
Output Condition | Transactional | Output Condition | OTC/PTP |  | Maria/Pablo | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 27 | TBD | [6 empty] | IDS Direct Connection |  | IDS | No |  |  |  | LSMW | [7 empty] | X
Product Listing and Exclusion | Master | PLE | OTC |  | Maria | Vivek | TBD | TBD | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 6 | TBD | [6 empty] | IDS Direct Connection |  | IDS | No |  |  |  | LSMW |  |  |  |  | X |  |  | X
Activity Cost Rate (Price) | Master | Rate | Finance |  | Leela | Leela | TBD | TBD | [11 empty] | IDS Direct Connection | File - Custom Program | IDS | No |  |  |  | LTMC |  |  | X | X | X
Activity Type | Transactional | Activity Type | Finance |  | Leela | Leela | TBD | TBD | [11 empty] | IDS Direct Connection |  | IDS | Yes | 24 | Unit test done |  | LTMC |  |  | X | X | X |  | X
Cost Center | Master | Cost Center | Finance/MD |  | Leela/Tom | Leela/Tom | 1 | 1 |  | SAP ECC | DRM | 3000 | 7000 | [6 empty] | IDS Direct Connection | File - Manual? | IDS | Yes | 62 | Unit test done |  | LTMC |  |  | X | X | X
Project | Transactional | Project | OTC |  | Maria | Vivek | TBD | TBD | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 10404 | TBD | [9 empty] | No | [8 empty] | X
Cost Element | Master | Account | Finance/MD |  | Leela/Tom | Leela/Tom | 1 | 1 | Grouped with GL Account S/4 Conversion Object | SAP ECC | Oracle EBS | 2500 | 5500 | [6 empty] | IDS Direct Connection |  | IDS | No |  |  |  | LTMC |  |  | X | X
Project Planned-Actual Costs | Transactional | Project | OTC |  | Maria | Vivek | TBD | TBD | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 4123443 | TBD | [9 empty] | No
GL Account/Master | Master | Account | Accounting |  | Tom | Tom | 1 | 1 |  | SAP ECC | Oracle EBS | 2500 | 5500 | [6 empty] | IDS Direct Connection |  | IDS | Yes | 65 | Unit test done |  | LTMC |  |  | X | X | X
Internal Order | Master | IO | Finance/Acctg |  | Leela/Tom | Leela/Tom | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | Yes | 67 | Unit test done |  | LTMC |  |  | X | X | X |  |  | X
Purchase Requisitions | Transactional | Purchase Order | PTP |  | Pablo | Pablo | 1 | 1 | [13 empty] | None | Yes |  |  |  | None |  |  | X | X
RAR - Accounting Contracts | Transactional | RAR | Accounting |  | Tom | Tom | 1 | TBD | Fiserv reviewing use of Dummy Contract (59999… 10-50% of total) | SAP ECC | Excel (if any… TBD) | 10000 | TBD | [8 empty] | None | No |  |  |  | SAP Std Program
RAR - Asset & Liability Balances | Transactional | RAR | Accounting |  | Tom | Tom | 1 | TBD |  | SAP ECC | Excel (if any… TBD) | 30000 | TBD | [8 empty] | None | No |  |  |  | SAP Std Program
RAR - Performance Obligations (POBs) | Transactional | RAR | Accounting |  | Tom | Tom | 1 | TBD | Determine Open Contract Line Items. Maria and team to pull something big picture. Billing and Rev. Rec. | SAP ECC | Excel (if any… TBD) | TBD | TBD | [8 empty] | None | No |  |  |  | SAP Std Program
Profit Center | Master | PC | Finance/MD |  | Leela/Tom | Leela/Tom | 1 | 1 | Somewhat Product based | SAP ECC | Oracle EBS & DRM | 400 | 500 | [6 empty] | IDS Direct Connection |  | IDS | Yes | 53 | Unit test done |  | LTMC |  |  | X | X | X
Assessments and Distribution | Transactional | Assessments | Finance |  | Leela | Leela | 1 | 1 | [11 empty] | IDS Direct Connection |  | IDS | No |  |  |  | Program | [7 empty] | X
Statistical Key Figure | Master | SKF Acct | Finance |  | Leela | Leela | 1 | 1 | [13 empty] | None | No |  |  |  | LTMC |  |  | X | X | X |  | X
Business Partner (Contact) | Master | Client | OTC |  | Maria | Vivek | 1 | 1 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 40708 | TBD | [6 empty] | IDS Direct Connection |  | IDS | No | Maybe customer rules can be resued | Need to be confirmed with functional |  | Program | [7 empty] | X
Employee | Master | Associate | Technical/MD |  | Roopa/Tom | Roopa | 1 | 1 | Tentative Plan - Interface from Workday instead of Conversion from ERP. FDC associates are in SAP ECC as well (needed for approval) | SAP ECC | SAP ECC | 22957 | 21800 | [6 empty] | IDS Direct Connection |  | IDS | No | Maybe customer rules can be resued | Need to be confirmed with functional |  | Program/ Interface
Employee - Contractor | Master | Associate | Technical/MD |  | Roopa/Tom | Roopa | 1 | 1 | Tentative Plan - Interface from Workday instead of Conversion from ERP. FDC associates are in SAP ECC as well (needed for approval) | SAP ECC | SAP ECC | 4819 | 10705 | [6 empty] | IDS Direct Connection |  | IDS | No | Maybe customer rules can be resued | Need to be confirmed with functional |  | Program/ Interface
Tax Invoice (Only Open) | Transactional | Tax | Tax |  | Leela | Leela | TBD | TBD | [14 empty] | No
WBS Element | Transactional | Projects | OTC |  | Maria | Vivek | 1 | 0 | Need Oracle Translator for FDC. | SAP ECC | Oracle EBS & DRM | 130973 | 0 | [6 empty] | IDS Direct Connection |  | IDS | No |  |  |  | SAP Std tcode |  |  |  |  | X |  |  | X

## Object List for IDS folders
Object List | IDS Folder Name
Accounts Receivable Open Item | Accounts Receivable Open Item
Bank Master | Bank Master
Condition Record for Pricing | Condition Record for Pricing
Customer | Customer
Bank - Balance | Bank - Balance
Customer Classification | Customer Classification
Fixed Assets (Incl Balances and Transactions) | Fixed Assets
Cash (Credit) Memo Record | Cash (Credit) Memo Record
Class | Class
Collections | Collections
Collections (Collectors) | Collections (Collectors)
Condition Contract - Rebate | Condition Contract - Rebate
GL Account Balance | GL Account Balance
COPA Assessments | COPA Assessments
COPA Derivation Rules | COPA Derivation Rules
COPA Value Fields | COPA Value Fields
GL Account Open Items | GL Account Open Items
Goods/Invoice Receipt (GR/IR) Open Items | Goods/Invoice Receipt (GR/IR) Open Items
Intercompany (IC) by Trading Partner | Intercompany (IC) by Trading Partner
Item Proposal | Item Proposal
Dispute Management Tables | Dispute Management Tables
Material | Material
Product (Material) BOM | Product (Material) BOM
Product Inventory IM (Finished) | Product Inventory IM (Finished)
Project Budget | Project Budget
Purchase Info Record with Conditions | Purchase Info Record with Conditions
Purchase Order (Open PO) | Purchase Order (Open PO)
Sales BOM | Sales BOM
Sales Contract | Sales Contract
Supplier (Vendor) | Supplier (Vendor)
Supplier Characteristic | Supplier Characteristic
Internal Order Activity | Internal Order Activity
Supplier Invoice (Only Open)/ AP Open | Supplier Invoice (Only Open)/ AP Open
Lease Related Items - CLM | Lease Related Items - CLM
EDI Partner (ALE) | EDI Partner (ALE)
Output Condition | Output Condition
Product Listing and Exclusion | Product Listing and Exclusion
Activity Cost Rate (Price) | Activity Cost Rate (Price)
Activity Type | Activity Type
Cost Center | Cost Center
Project | Project
Cost Element | Cost Element
Project Planned-Actual Costs | Project Planned-Actual Costs
GL Account/Master | GL Account/Master
Internal Order | Internal Order
Purchase Requisitions | Purchase Requisitions
RAR - Accounting Contracts | RAR - Accounting Contracts
RAR - Asset & Liability Balances | RAR - Asset & Liability Balances
RAR - Performance Obligations (POBs) | RAR - Performance Obligations (POBs)
Profit Center | Profit Center
Assessments and Distribution | Assessments and Distribution
Statistical Key Figure | Statistical Key Figure
Business Partner (Contact) | Business Partner (Contact)
Employee | Employee
Employee - Contractor | Employee - Contractor
Tax Invoice (Only Open) | Tax Invoice (Only Open)
WBS Element | WBS Element

## Look ups
Owners
Area | Owner
PTP | Pablo
Treasury | Pablo
Finance | Leela
Tax | Leela
OTC | Maria
Accounting | Tom
MD | Tom
Technical | Roopa
Finance/MD | Leela/Tom
OTC/PTP | Maria/Pablo
Finance/Acctg | Leela/Tom
OTC/MD | Maria/Tom
Technical/MD | Roopa/Tom
Open Text | Out-of-Scope
Treasury/Acctg | Pablo/Tom

## Original (hidden)
S/4HANA Data Object |  |  |  | Phase 0 - Need to Know Items | [6 empty] | Phase 0 - Nice to Know Items | [5 empty] | Explore Items |  |  |  | Available Load Method
|  |  |  | Data Conversion Scope |  |  |  |  | Source System |  | Data Volume |  | Extract Method to S/4 Template |  | Quality Tool | Load Tool | Relevancy Rules |  | Cleansing Packages
Object | Data Type | Object Group | Area | FSV | FDC | FSV Owner | FDC Owner | Notes | FSV | FDC | FSV | FDC | FSV | FDC | Profile | Load to S/4 | FSV | FDC | FSV | FDC | IDS | IDoc | LTMC | Direct | Manual | Program | LSMW
Open Text Archive - OTC - Attachments (Open Text is not used for OTC) | Transactional | Open Text | OTC | 0 | 0 | Maria | Vivek | Out of Scope for S/4 Data Conversion. Open Text engagement is separate. | SAP ECC |  | N/A |  |  |  | None
VC - Characteristics Group | Master | ?? | ?? | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Historical Balance (Restricted) | Transactional | Account | Accounting | 0 | 0 | Tom |  | Journal Forced Balance | SAP ECC | Oracle EBS | [12 empty] | X
COPA Characteristics | Master | COPA | Finance | 0 | 0 | Leela | [19 empty] | X
Customer Hierarchy | Master | Client | Finance | 0 | 0 | Leela |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Customer Material Info Record | Master | S Material | OTC | 0 | 0 | Maria |  |  | SAP ECC | Oracle EBS | 0 |  |  |  |  | Winshuttle |  |  |  |  | X | X | X |  |  | X
Deliveries (Open) | Transactional |  | OTC | 0 | 0 | Maria |  |  | SAP ECC | Oracle EBS | 335 | [9 empty] | X | X
Quotation | Transactional | S Quote | OTC | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Sales Order (Open SO) | Transactional | S Order | OTC | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Service Order (Open SRVO) | Transactional | S Order | OTC | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
VC - Configuration Profile | Master | Material | OTC | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
VC - Material Variant | Master | Material | OTC | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Characteristic | Master | Client | OTC/MD | 0 | 0 | Maria/Tom |  |  | SAP ECC | Oracle EBS | 364 | [9 empty] | X | X | X
Procurement Alternatives | Master |  | PTP | 0 | 0 | Pablo
Open Text Archive - PTP - Invoice Copies | Transactional | Open Text | PTP | 0 | 0 | Pablo |  | Out of Scope for S/4 Data Conversion. Open Text engagement is separate. | [6 empty] | None
Purchase Contract | Transactional | P Contract | PTP | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Service | Master |  | PTP | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X |  |  |  | X
Open Text Archive - RTR - Invoice Review | Transactional | Open Text | RTR | 0 | 0 |  |  | Out of Scope for S/4 Data Conversion. Open Text engagement is separate. | [6 empty] | None
Bank - Orders (Open) | Transactional | Bank | Treasury | 0 | 0 | Pablo | [16 empty] | X |  | X | X
Batch | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Batch Characteristic | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Batch Class | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Batch Derivation | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Batch Determination | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Batch Search Strategies | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Bin | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Bin Fixed Assignment | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Bin Parking Location | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Bin Sort | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Bin Storage Conversion | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Business Partner (EWM Users) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Business Process | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Catalog Code Group/Code | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Certificate Assignments | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Certificate of Analysis/Compliance (CoA/CoC) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Certificate Profiles | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Certificate Recipients | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Certificate Sales Specs | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Change Master | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Consent | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Control Cycle - Kanban | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Cost Center Plans | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Customer - Extend with Credit Management | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X |  |  | X
Document Info Record | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
EHS - Dangerous Goods (DG) Assessment for Product | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
EHS - Location | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
EHS - Location Hierarchy | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
EHS - Material Specification | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Cost Center Group | Configuration |  |  | 1 | 1 | #N/A | [8 empty] | None | Config
EHS - PSS - Product Compliance Info | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
EHS - PSS - Raw Material Compliance Info | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
EHS - PSS - Substance | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
EHS - Substance Volume Tracking (SVT) - Cumulative | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Equipment | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Equipment BOM | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Equipment Characteristic | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Equipment Class | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Equipment Task List | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X |  |  |  | X
Export Control Classification Numner (ECCN) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Framework Order | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Functional Location | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Functional Location BOM | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Functional Location Classes | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Functional Location Task List | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X |  |  |  |  | X
GTS - BWh Stock Upload | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
GTS - Custom Mgmt - Auth - Admitted Ship. & Rec. | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
GTS - Legal Reg. Embargo | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
GTS - License Master | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
GTS - Material Master Data Enrichment (GTS) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Harmonized Tariff Schedule (HTS) Codes | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
IBAU Assembly BOM | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Inspection Catalogs (PM) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Inspection Catalogs (QM) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Inspection Characteristics | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Inspection Method | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Inspection Method - Classification | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Inspection Plan | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Inspection Plan - Dynamic Modification Rules (DMR) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Inspection Setup | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Exchange Rate | Configuration |  | Treasury/Acctg | 1 | 1 | Pablo/Tom | [8 empty] | None | Config |  |  |  |  | X | X | X
Inspection Type | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
JIT - Customer | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
JIT - Package Group | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
JIT - Supply Control | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
JVA - Cost Center Suspense | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
JVA - Joint Operating Agreement | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
JVA - Joint Venture Master | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
JVA - Joint Venture Partner | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
JVA - Project Suspense | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
JVA - Venture Suspense | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Legal Transaction | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Maintenance Item | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Maintenance Item - Extend with Long Text | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Maintenance Notification | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Maintenance Order | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Maintenance Plan | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Maintenance Task List | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X |  |  |  | X
Maintenance, Repair, and Overhaul (MRO) BOMs | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Maintenance, Repair, and Overhaul (MRO) Product Memo Text | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Measurement Document | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Measuring Point | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X |  |  | X
Network | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Object Classification - General | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Object Dependency | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Order Reservation | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Outline Agreements (Contracts - Commissions, Scheduling, etc.) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Phrases | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Planned Independent Requirements | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Process Order | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Product - EWM View | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Product - Forecast Planning | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Product Classification | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Product Consumption | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Product Determination | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Product Handling Units | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Product Inventory WM (Finished) | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Product Ledger Controlling Level | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Production Order | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X |  |  |  | X
Production Version | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Profit Center Plan | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Quality Info Record | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Quality Notifications | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Radio Frequency (RF) Device User | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Recipe | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Recipe (Mixing Ratios) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Reference Operation Set | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Routing | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Routing - Rate | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Routing - Reference Rate | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Sales Order Mgmt (SOM) Compliance & Regulatory | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Sales Order Text - Multi Languages | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Sampling Procedure | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [14 empty] | X
Selected Set | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Selected Set Code | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Software/Hardware Constraint | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X
Stock Transfer Order | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Storage Units | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Supplier - Extend with New Org Levels | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [12 empty] | X
Transportation Shipments | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Transportation Units (Vehicles) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
Valuation Set (Price) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS
WBS Element - Planning and Budget Distribution | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Work Center (Resource/Capacity) | Master |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [10 empty] | X | X | X
Work Orders - PM (Open) | Transactional |  |  | 0 | 0 |  |  |  | SAP ECC | Oracle EBS | [15 empty] | X
Fixed Asset (Incl. Balances and Transactions) | Transactional | Fixed Asset | Accounting | 1 | 1 | Tom | Tom |  | SAP ECC | Oracle EBS, Excel (CIP) |  |  |  |  | IDS | IDS |  |  |  |  | X | X | X
GL Account | Master | Account | Accounting | 1 | 1 | Tom | Tom |  | SAP ECC | Oracle EBS | 2500 | 5500 |  |  | IDS | LTMC |  |  |  |  | X | X | X
GL Account Balance and Open Items | Transactional | Account | Accounting | 1 | 1 | Tom | Tom |  | SAP ECC | Oracle EBS | 2500 | 5500 |  |  | IDS | IDS |  |  |  |  | X | X | X
Intercompany (IC) by Trading Partner | Master | Intercompany | Accounting | 1 | 1 | Tom | Tom | [7 empty] | IDS | IDS
RAR - Accounting Contracts | Transactional | RAR | Accounting | 1 | TBC | Tom | Tom | Fiserv reviewing use of Dummy Contract (59999… 10-50% of total) | SAP ECC | Excel (if any… TBD) | 10000 |  |  |  | None
RAR - Asset & Liability Balances | Transactional | RAR | Accounting | 1 | TBC | Tom | Tom |  | SAP ECC | Excel (if any… TBD) | 30000 |  |  |  | None
Output Determination | Configuration |  | OTC/PTP | 1 | 1 | Maria/Pablo | [8 empty] | None | Config
RAR - Performance Obligations (POBs) | Transactional | RAR | Accounting | 1 | TBC | Tom | Tom | Determine Open Contract Line Items. Maria and team to pull something big picture. Billing and Rev. Rec. | SAP ECC | Excel (if any… TBD) |  |  |  |  | None
Assessments and Distribution | Transactional | Assessments | Finance | 1 | 1 | Leela | Leela | [7 empty] | IDS | Program | [9 empty] | X
Project Budget | Master | IO | Finance | 1 | 1 | Leela | Leela | [7 empty] | IDS | IDS
Statistical Key Figure | Master | SKF Acct | Finance | 1 | 1 | Leela | Leela | [7 empty] | None | LTMC |  |  |  |  | X | X | X |  | X
Internal Order | Master | Fixed Asset | Finance/Acctg | 1 | 1 | Leela/Tom | Leela/Tom | [7 empty] | IDS | LTMC |  |  |  |  | X | X | X |  |  | X
Internal Order Activity | Transactional | IO | Finance/Acctg | 1 | 1 | Leela/Tom | Leela/Tom | [13 empty] | X | X | X |  |  | X
Cost Center | Master | Cost Center | Finance/MD | 1 | 1 | Leela/Tom | Leela/Tom |  | SAP ECC | DRM | 3000 | 7000 |  | File - Manual? | IDS | LTMC |  |  |  |  | X | X | X
Cost Element | Master | Account | Finance/MD | 1 | 1 | Leela/Tom | Leela/Tom |  | SAP ECC | Oracle EBS | 2500 | 5500 |  |  | IDS | LTMC |  |  |  |  | X | X
Profit Center | Master | PC | Finance/MD | 1 | 1 | Leela/Tom | Leela/Tom | Somewhat Product based | SAP ECC | Oracle EBS & DRM | 400 | 500 |  |  | IDS | LTMC |  |  |  |  | X | X | X
Customer Classification | Master | Client | MD | 1 | 1 | Tom | Tom | FDIC # (Class) | [6 empty] | IDS | IDS |  |  |  |  | X | X
Accounts Receivable Open Item | Transactional | AR | OTC | 1 | 1 | Maria | Vivek |  | SAP ECC | Oracle EBS | 11,382,229 (as of 11/18) | 27000 | Direct Connection | File - Standard Program | IDS | IDS | X |  |  |  | X | X | X
Business Partner (Contact) | Master | Client | OTC | 1 | 1 | Maria | Vivek |  | SAP ECC |  | 40708 |  |  |  | IDS | Program | [9 empty] | X
Collections (Collectors) | Master | Collections | OTC | 1 | 0 | Maria | Vivek |  |  |  | 30 | 0
Condition Record for Pricing | Master | Condition Record | OTC | 1 | 1 | Maria | Vivek |  | SAP ECC |  | 306636 |  |  |  | IDS | IDS |  |  |  |  | X | X | X
Dispute Management Tables | Master | FSCM | OTC | 1 | 1 | Maria | Vivek |  | SAP ECC |  | 17685 |  |  |  |  | Program
Sales BOM | Master | S Material | OTC | 1 | 1 | Maria | Vivek |  | SAP ECC |  | 0 |  |  |  | IDS | IDS |  |  |  |  | X | X
Sales Contract | Transactional | Contract | OTC | 1 | 1 | Maria | Vivek |  | SAP ECC |  | 161877 |  |  |  | IDS | IDS |  |  |  |  | X | X | X
Sales Pricing (Is this a duplicate row 45) | Master | Pricing | OTC | 1 | 1 | Maria | Vivek |  | SAP ECC |  | N/A |  |  |  | IDS | IDS |  |  |  |  | X | X |  |  |  | X
WBS Element | Transactional | Projects | OTC | 1 | 0 | Maria | Vivek |  | SAP ECC |  | 130973 |  |  |  | IDS | SAP Std tcode | [6 empty] | X |  |  | X
Class | Master | Client/Vendor | OTC/MD | 1 | 1 | Maria/Tom | Vivek |  | SAP ECC |  | 34 | [9 empty] | X | X | X
Customer | Master | Client | OTC/MD | 1 | 1 | Maria/Tom | Vivek | Excel/DRM/IDW/UFO | SAP ECC | Oracle EBS | 20000 | 7000 |  |  | IDS | IDS |  |  |  |  | X | X | X
Profit Center Group | Configuration | PC | Finance/MD | 1 | 1 | Leela/Tom | [8 empty] | None | Config |  |  |  |  | X | X
Output Condition | Transactional | Output Condition | OTC/PTP | 1 | 1 | Maria/Pablo | Vivek |  | SAP ECC |  | 27 |  |  |  | IDS | LSMW | [9 empty] | X
Product (Material) | Master | P Material | OTC/PTP | 1 | 1 | Maria/Pablo | Vivek |  | SAP ECC |  | 68597 |  |  |  | IDS | IDS |  |  |  |  | X | X | X
Product (Material) BOM | Master | Reseller | OTC/PTP | 1 | 1 | Maria/Pablo | Vivek |  | SAP ECC |  | 231 |  |  |  | IDS | IDS |  |  |  |  | X | X | X
Product Inventory Balance/Validation (Is this a duplicate of row 160?) | Transactional | Reseller | OTC/PTP | 1 | 1 | Maria/Pablo | Vivek | Small amount of inventory is maintained | SAP ECC |  | N/A |  |  |  | None | None |  |  |  |  | X | X | X
Product Inventory IM (Finished) | Transactional | Reseller | OTC/PTP | 1 | 1 | Maria/Pablo | Vivek |  | SAP ECC |  | 3682 |  |  |  | IDS | IDS |  |  |  |  | X | X
Goods Receipt / Inovice Receipt (GR/IR) Open Items | Transactional | GRIR | PTP | 1 | 1 | Pablo | Pablo | [7 empty] | IDS | IDS |  |  |  |  | X | X
Purchase Info Record with Conditions | Master | P Material | PTP | 1 | 1 | Pablo | Pablo | [7 empty] | IDS | IDS |  |  |  |  | X | X | X
Purchase Order (Open PO) | Transactional | Purchase Order | PTP | 1 | 1 | Pablo | Pablo | [7 empty] | IDS | IDS |  |  |  |  | X | X | X
Purchase Requisitions | Transactional | Purchase Order | PTP | 1 | 1 | Pablo | Pablo | [7 empty] | None | None |  |  |  |  | X | X
Supplier (Vendor) | Master | Vendor | PTP | 1 | 1 | Pablo | Pablo | [7 empty] | IDS | IDS |  |  |  |  | X | X | X
Supplier Characteristic | Master | Vendor | PTP | 1 | 1 | Pablo | Pablo | [7 empty] | IDS | IDS |  |  |  |  | X | X
EDI Partner (ALE) | Transactional | Technical | Technical | 1 | 0 | Roopa | Roopa |  | SAP ECC | N/A | 39 | 0 |  |  | IDS | LSMW | [9 empty] | X
Employee | Master | Associate | Technical/MD | 1 | 1 | Roopa/Tom | Roopa | Tentative Plan - Interface from Workday instead of Conversion from ERP. FDC associates are in SAP ECC as well (needed for approval) | SAP ECC | SAP ECC | 22957 | 21800 |  |  | IDS | Program/ Interface
Employee - Contractor | Master | Associate | Technical/MD | 1 | 1 | Roopa/Tom | Roopa | Tentative Plan - Interface from Workday instead of Conversion from ERP. FDC associates are in SAP ECC as well (needed for approval) | SAP ECC | SAP ECC | 4819 | 10705 |  |  | IDS | Program/ Interface
Bank Master | Master | Bank | Treasury | 1 | 1 | Pablo | Pablo | [7 empty] | IDS | IDS |  |  |  |  | X | X | X |  | X | X
COPA Assessments | Master | COPA | Finance | TBC | TBC | Leela | Leela | [18 empty] | X
COPA Derivation Rules | Master | COPA | Finance | TBC | TBC | Leela | Leela | [18 empty] | X
COPA Value Fields | Master | COPA | Finance | TBC | TBC | Leela | Leela | [18 empty] | X
Item Proposal | Transactional | Item Proposal | OTC | TBC | TBC | Maria | Vivek |  | SAP ECC |  | 0 |  |  |  | IDS | IDS | [9 empty] | X
Product Listing and Exclusion | Master | PLE | OTC | TBC | TBC | Maria | Vivek |  | SAP ECC |  | 6 |  |  |  | IDS | LSMW | [6 empty] | X |  |  | X
Project | Transactional | Project | OTC | TBC | TBC | Maria | Vivek |  | SAP ECC |  | 10404 | [11 empty] | X
Project Planned-Actual Costs | Transactional | Project | OTC | TBC | TBC | Maria | Vivek |  | SAP ECC
Supplier Invoice (Only Open) | Transactional | Invoice | PTP | TBC | TBC | Pablo | Pablo | [7 empty] | IDS | IDS |  |  |  |  | X | X
Tax Invoice (Only Open) | Transactional | Tax | Tax | TBC | TBC | Leela | Leela
Cash (Credit) Memo Record | Transactional | Bank | Treasury | TBC | TBC | Pablo | Pablo | [13 empty] | X | X | X
Collections | Transactional | Collections |  | TBC | TBC
Lease Related Items - CLM | Transactional | CLM |  | TBC | TBC | [9 empty] | None
Source List | Configuration | P Material | PTP | 1 | 1 | Pablo | [8 empty] | None | Config |  |  |  |  | X | X | X
Bank - Balance | Transactional | Bank | Accounting | TBD | TBD | Tom | Tom | Uncleared Checks | [14 empty] | X |  |  | X
Activity Cost Rate (Price) | Master | Rate | Finance | TBD | TBD | Leela | Leela |  | SAP ECC | Oracle EBS |  |  | Direct Connection | File - Custom Program | IDS | LTMC | X |  |  |  | X | X | X
Activity Type | Transactional | Activity Type | Finance | TBD | TBD | Leela | Leela | [7 empty] | IDS | LTMC |  |  |  |  | X | X | X |  | X
Class Hierarchy | Master | [19 empty] | X | X | X
Condition Contract | Master | [21 empty] | X
Condition Contract - Rebate | Master
Company Code | Configuration |  |  | 1 | 1 | #N/A
Plant | Configuration |  |  | 1 | 1 | #N/A
Product Hierarchy | Configuration |  |  | 1 | 1 | #N/A
Sales Area / Group | Configuration |  |  | 1 | 1 | #N/A