## Jump Server details
RDP
Computer | 10.20.255.36
User name | fftadmin1
Password | A3#{[S(&D3Ex4D3WXQ2)6Ky%L5]}&
Data Services Designer
System | vhjeldd1sbo01:6400
Username | <Use respective user names same as HEC For eg. DD1_DS_LR_01>
Password | <Use respective password same as HEC For eg. DD1_DS_LR_01>
DSMC | http://10.20.65.70:8080/DataServices
CMC | http://10.20.65.70:8080/BOE/CMC
Information Steward | http://10.20.65.70:8080/BOE/InfoSteward

## Test case summary
Seq | Category | Work/Activity | Responsible | Effort | Date/Time | Status | Comments
6 | Post Migration | Validate access to Data Services Designer, IS and CMC | DATA Team | 15 mins per Developer | 2021-03-01 | In Progress | Completed for JET, Passport and EDM
6 | Post Migration | BODS - Validate availability of code in Local and Central repositories | DATA Team | 1 hr per repository | 2021-03-01 | In Progress | Completed for JET, Passport and EDM
6 | Post Migration | BODS - Validate datastore connections for each project | DATA Team | 1 hr per repository | 2021-03-01 | In Progress | Completed for JET, Passport and EDM
6 | Post Migration | BODS - Execute jobs using all source and target systems for each project | DATA Team | ~ 6 hrs | 2021-03-01 | In Progress | Completed for JET, Passport and EDM
6 | Post Migration | BODS - Check out and Check in code into Central repository from Local | DATA Team | 1 hr per project | 2021-03-01 | In Progress | Pending open issue on MSR to update permission for all objects as its currently in "Read' only mode
6 | Post Migration | BODS - Import/Export code using ATL files | DATA Team | 1 hr per project | 2021-03-01 | In Progress | Completed for JET, Passport and EDM
7 | Post Migration | BODS - Setup job schedules and Test the same | DATA (Finance First) | 1 hr | 2021-03-01 | Not Started

## Test case details
SR No. # | Category | Work/Activity | Responsible | Effort | Status | Comments
4 | Post-Migration | Validate access to Data Services Designer | Preethi (JET, Passport), Mike (EDM), Nishanth (Finance First) | 15 mins per Developer
5 | Post-Migration | Validate if Local object library is available with the latest code and datastore connections | DATA team Developers | 1 hr per repository
6 | Post-Migration | Validate access to Central repository by activating the same from each local repository | DATA team Developers | 30 mins per repository
7 | Post-Migration | Validate if latest code is available in Central repository - One time activity only for DD1 | Preethi (JET, Passport), Mike (EDM), Nishanth (Finance First) | 1 hr per project
8 | Post-Migration | Validate datastore connections for each project | Preethi (JET, Passport), Mike (EDM), Nishanth (Finance First) | 1 hr per project
9 | Post-Migration | Execute jobs using all source and target systems for each project | DATA team Developers
9.4 | Post-Migration | Finance First | Nishanth | TBD
9.4.1 | Post-Migration | Execute job to create/populate tables in BODS SQL Server Staging databases |  | 15 mins
9.4.2 | Post-Migration | Execute job to read data from Excel file in SAP App server |  | 15 mins
9.4.3 | Post-Migration | Execute job to read and write data into Text file in SAP App server |  | 15 mins
9.4.4 | Post-Migration | Execute job to read data from SAP CFIN |  | 15 mins
9.4.5 | Post-Migration | Execute job to load data into SAP CFIN |  | 15 mins
9.4.6 | Post-Migration | Execute job to read data into SAP FF MDG |  | 15 mins
9.4.7 | Post-Migration | Execute job to load data into SAP FF MDG |  | 15 mins
9.4.8 | Post-Migration | Execute job to load data into SAP SLT |  | 15 mins
9.4.9 | Post-Migration | Execute job to enrich Address data using DQM microservices |  | 15 mins
9.4.10 | Post-Migration | Execute job to read data from Legacy SAP ECC Austria |  | 15 mins |  | Connection not being used anymore and not working on HEC
9.4.11 | Post-Migration | Execute job to read data from Legacy IFAS Mainframe/Linked SQL server/ODBC/Files |  | 15 mins
9.4.12 | Post-Migration | Execute job to read data from Legacy Norway Axapta/ORACLE |  | 15 mins |  | Not needed
9.4.13 | Post-Migration | Execute job to read data from Legacy Sweden Axapta3/ORACLE |  | 15 mins |  | Not needed
9.4.14 | Post-Migration | Execute job to read data from Legacy Sweden Axapta/SQL Server |  | 15 mins
9.4.15 | Post-Migration | Execute job to read data from Legacy Denmark Axapata3/Oracle |  | 15 mins |  | Not needed
9.4.16 | Post-Migration | Execute job to read data from Legacy Denmark XAL/Oracle |  | 15 mins
9.4.17 | Post-Migration | Execute job to read data from TITAN stfiber db |  | 15 mins
9.4.18 | Post-Migration | Execute job to read data from TITAN btfiber db |  | 15 mins
9.4.19 | Post-Migration | Execute job to read data from TITAN stcaradco db |  | 15 mins
9.4.20 | Post-Migration | Execute job to read data from TITAN btcaradco db |  | 15 mins
9.4.21 | Post-Migration | Execute job to read data from TITAN stcorpref db |  | 15 mins
9.4.22 | Post-Migration | Execute job to read data from TITAN btcorpref db |  | 15 mins
9.4.23 | Post-Migration | Execute job to read data from TITAN stdcan db |  | 15 mins
9.4.24 | Post-Migration | Execute job to read data from TITAN btdcan db |  | 15 mins
9.4.25 | Post-Migration | Execute job to read data from TITAN stdonat2 db |  | 15 mins
9.4.26 | Post-Migration | Execute job to read data from TITAN btdonat2 db |  | 15 mins
9.4.27 | Post-Migration | Execute job to read data from TITAN stdr db |  | 15 mins
9.4.28 | Post-Migration | Execute job to read data from TITAN btdr db |  | 15 mins
9.4.29 | Post-Migration | Execute job to read data from TITAN stediroute db |  | 15 mins
9.4.30 | Post-Migration | Execute job to read data from TITAN btediroute db |  | 15 mins
9.4.31 | Post-Migration | Execute job to read data from TITAN stflush db |  | 15 mins
9.4.32 | Post-Migration | Execute job to read data from TITAN btflush db |  | 15 mins
9.4.33 | Post-Migration | Execute job to read data from TITAN stjeldwen db |  | 15 mins
9.4.34 | Post-Migration | Execute job to read data from TITAN btjeldwen db |  | 15 mins
9.4.35 | Post-Migration | Execute job to read data from TITAN stjwis db |  | 15 mins
9.4.36 | Post-Migration | Execute job to read data from TITAN btjwis db |  | 15 mins
9.4.37 | Post-Migration | Execute job to read data from TITAN stnorco db |  | 15 mins
9.4.38 | Post-Migration | Execute job to read data from TITAN btnorco db |  | 15 mins
9.4.39 | Post-Migration | Execute job to read data from TITAN stpozzi db |  | 15 mins
9.4.40 | Post-Migration | Execute job to read data from TITAN btpozzi db |  | 15 mins
9.4.41 | Post-Migration | Execute job to read data from TITAN stprem db |  | 15 mins
9.4.42 | Post-Migration | Execute job to read data from TITAN btprem db |  | 15 mins
9.4.43 | Post-Migration | Execute job to read data from TITAN streman db |  | 15 mins
9.4.44 | Post-Migration | Execute job to read data from TITAN btreman db |  | 15 mins
9.4.45 | Post-Migration | Execute job to read data from TITAN stsummit db |  | 15 mins
9.4.46 | Post-Migration | Execute job to read data from TITAN btsummit db |  | 15 mins
9.4.47 | Post-Migration | Execute job to read data from TITAN stunited db |  | 15 mins
9.4.48 | Post-Migration | Execute job to read data from TITAN btunited db |  | 15 mins
9.4.49 | Post-Migration | Execute job to read data from TITAN stwenco2 db |  | 15 mins
9.4.50 | Post-Migration | Execute job to read data from TITAN btwenco2 db |  | 15 mins
9.4.51 | Post-Migration | Execute job to read data from TITAN stwfs db |  | 15 mins
9.4.52 | Post-Migration | Execute job to read data from TITAN btwfs db |  | 15 mins
9.4.53 | Post-Migration | Execute job to read data from TITAN stwillmar db |  | 15 mins
9.4.54 | Post-Migration | Execute job to read data from TITAN btwillmar db |  | 15 mins
9.4.55 | Post-Migration | Execute job to read data from TITAN stwin1 db |  | 15 mins
9.4.56 | Post-Migration | Execute job to read data from TITAN btwin1 db |  | 15 mins
9.4.57 | Post-Migration | Execute job to read data from TITAN stwnedirout db |  | 15 mins
9.4.58 | Post-Migration | Execute job to read data from TITAN btwnedirout db |  | 15 mins
9.4.59 | Post-Migration | Execute job to read data from TITAN stfrancep db |  | 15 mins
9.4.60 | Post-Migration | Execute job to read data from TITAN stjweuro db |  | 15 mins
9.4.61 | Post-Migration | Execute job to read data from TITAN stukdoor db |  | 15 mins
9.4.62 | Post-Migration | Execute job to read data from TITAN depcorinthn db |  | 15 mins
9.4.63 | Post-Migration | Execute job to read data from TITAN depcorpaus db |  | 15 mins
9.4.64 | Post-Migration | Execute job to read data from TITAN depstegbar db |  | 15 mins
10 | Post-Migration | Check out and Check in code into Central repository from Local |  | 15 mins
11 | Post-Migration | Import an ATL File into local repository |  | 15 mins
12 | Post-Migration | Export code as an ATL file from local repository |  | 15 mins
13 | Post-Migration | Setup job schedules in DSMC |  | 15 mins

## ATL Exports List
DD1_DS_CR_03 - Finance First |  |  |  | DD1_DS_LR_21 - Nishanth Patibandla |  |  |  | DD1_DS_LR_22 - Karthikeyan Ganesan |  |  |  | DD1_DS_LR_23 - Revathi Bharathi |  |  |  | DD1_DS_LR_26 - Sabana S |  |  |  | DD1_DS_LR_28 - Prasad Attur
Seq | Category | ATL File Name | Import Status | Seq | Category | ATL File Name | Import Status | Seq | Category | ATL File Name | Import Status | Seq | Category | ATL File Name | Import Status | Seq | Category | ATL File Name | Import Status | Seq | Category | ATL File Name | Import Status
1 | Connection | FF_DEV_DATA_STORES_V3.atl | Yes | 1 | Connection | FF_DEV_DATA_STORES_V3.atl | Yes | 1 | Connection | FF_DEV_DATA_STORES_V3.atl | Yes | 1 | Connection | DD1_DS_LR_23_Datastore.atl | Yes | 1 | Connection | FF_DEV_DATA_STORES_V3.atl | Yes | 1 | Connection | FF_DEV_DATA_STORES_V3.atl | Yes
2 | Code - Project | FF_CONV_BASWARE_PO.atl | Yes | 2 | Code - Project | DD1_DS_LR_21_Project_Basware_Export.atl | Yes | 2 | Code - Project | DD1_DS_LR_22_Project_Customer_Master_Export.zip | Yes | 2 | Code - Project | DD1_DS_LR_23_FF_CONV_BASWARE_PO.atl | Yes | 2 | Code - Project | FF_R2R_C005_GL_AP_AR_INIT.atl | Yes | 2 | Code - Project | DD1_DS_LR_28_Project_Basware_Export.zip | Yes
2 | Code - Project | FF_CONV_OTC_C002_CUSTOMER_MASTER.zip | Yes | 2 | Code - Project | DD1_DS_LR_21_Project_Customer_Master_Export.atl | Yes | 2 | Code - Project | DD1_DS_LR_22_Project_JET_CM_Export.zip | Yes | 2 | Code - Project | DD1_DS_LR_23_FF_CONV_P2P_C004_VENDOR_MASTER.zip | Yes | 2 | Code - Project | FF_R2R_I009_TRANS_GL_AP_AR.atl | Yes | 2 | Code - Project | DD1_DS_LR_28_Project_FF_Export.atl | Yes
2 | Code - Project | FF_CONV_P2P_C004_VENDOR_MASTER.zip | Yes | 2 | Code - Project | DD1_DS_LR_21_Project_Open_PO_Export.atl | Yes |  |  |  |  | 2 | Code - Project | DD1_DS_LR_23_FF_CONV_R2R_C001_FIXED_ASSETS.atl | Yes | 2 | Code - Project | FF_R2R_I009_TRANS_GL_AP_AR_BKP.atl | Yes | 2 | Code - Project | DD1_DS_LR_28_Project_Open_PO_Export.atl | Yes
2 | Code - Project | FF_CONV_P2P_C007_OPEN_PURCH_ORDER.atl | Yes | 2 | Code - Project | DD1_DS_LR_21_Project_P1GB_Trans_Export.atl | Yes | [8 empty] | 2 | Code - Project | FF_R3_R2R_I027_TRANS_GL_AP_AR.atl | Yes | 2 | Code - Project | DD1_DS_LR_28_Project_P1GB_Trans_Export.atl | Yes
2 | Code - Project | FF_CONV_R2R_C001_FIXED_ASSETS.atl | Yes | [12 empty] | 2 | Code - Project | PROJ_TRAINING.atl | Yes | 2 | Code - Project | DD1_DS_LR_28_Project_Titan_APInvoices_Export.atl | Yes
2 | Code - Project | FF_R2_CONV_BASWARE_PO_REPLICATE.zip | Yes | [12 empty] | 2 | Code - Project | TEST_PROJ.atl | Yes | 2 | Code - Project | DD1_DS_LR_28_Project_Titan_Export.atl | Yes
2 | Code - Project | FF_R2_R2R_I009_TRANS_GL_AP_AR.atl | Yes
2 | Code - Project | FF_R2R_C005_GL_AP_AR_INIT.atl | Yes
2 | Code - Project | FF_R2R_I009_TRANS_GL_AP_AR.atl | Yes
2 | Code - Project | FF_R3_R2R_I027_TRANS_GL_AP_AR.atl | Yes